These Notification templates are provided for use on City of Kansas City, MO Public Improvement Projects in order to verify locations of existing as well as proposed utilities that may be in conflict with the Project.

The Public Improvement Notices should be prepared and distributed to the utilities by the Project designer.  Each Public Improvement Notice shall include the KCMO logo and the contact information of the originating department/division that is managing the Project.

Each of the four (4) Public Improvement Notices is different and intended to achieve the following objectives:

Public Improvement Notice 1 // Initial Notification

Objective: To notify utilities that a Project is underway and to define the general Project location.

Public Improvement Notice #1 is for use on all projects as initial notification to all utility companies that may have assets or interests within the identified Project area. This notice acknowledges the various utilities in the area and requests supporting information (maps, etc.) for existing or proposed assets/facilities in order to accurately depict them on the Project plans. This notice should be sent early in the project, prior to initiating the field survey.

Public Improvement Notice #2 // Preliminary Design Phase Notification

Objective: To facilitate confirmation from utilities that their assets/facilities are shown in the correct location on the plans.

Objective: To define the preliminary alignment and grade of the Project and check for potential utility conflicts.

This Notice should be sent to all utilities that replied in the affirmative on Public Improvement Notice #1, or, did not respond at all.  This notice is for use on all projects to verify utility locations of record in both plan and profile views. This notice requests that the utility company verify the location of record and the size of asset that has been depicted on the drawings.

Public Improvement Notice #2 also requests that, if the actual location is different from that which is shown on the drawings, the utility provide specific location records.  If the utility does not have an identified conflict, this form's response serves as verification that they have no known conflict with the Project.

Public Improvement Notice #2 should be sent as many times as it takes until there is confirmation that the Project plans depict the assets/facilities in their location of record.

Public Improvement Notice #3 // Utility Relocation Notification

Objective: To request detailed utility relocation plans and schedule for the assets/facilities that have been identified as being in conflict with the Project.

If it is determined that the relocation of a utility is required, then Public Improvement Notice #3 is needed.  Public Improvement Notice #3 initiates the process of the utility company preparing relocation plans and scheduling construction of the relocation of their facilities/assets.

Public Improvement Notice #4 // Notification of Pending Construction

Objective: To notify utilities that construction is imminent and their inaction will have potential legal consequences.

The fourth notice is to be treated as the FINAL notification that the utility has assets/facilities that are in conflict with the Project and they must relocate them by a specific date or face legal action by the City.